## Agile Product Backlog
AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
|  |  | Marzolo, Oro, Pagliara, Policastro |  |  |  | Yes |  | Complete | 52 |  | This section is for the drop-down list
1 | Users' management | Sprint 1 | " " | 2020-11-21 | 2020-11-26 | Yes |  | High | Complete | 21 | Yes | Yes | High | Complete
2 | Role's assignment | Sprint 1 | " " | 2020-11-25 | 2020-11-27 | Yes |  | High | Complete | 2 | Yes | No | Medium | In Progress
3 | Maintainers' competences' assignment | Sprint 1 | " " | 2020-11-25 | 2020-11-29 | Yes |  | High | Complete | 5 | Yes |  | Low | Not Started
9 | Activities' management | Sprint 1 | " " | 2020-11-27 | 2020-11-30 | Yes |  | High | Complete | 17 | Yes
10 | Activities List's visualization | Sprint 1 | " " | 2020-11-28 | 2020-11-29 | Yes |  | High | Complete | 5 | Yes
7 | Accesses log | Sprint 1 | " " | 2020-11-26 | 2020-11-29 | Yes |  | Low | Complete | 2 | Yes
|  |  | Marzolo, Oro, Pagliara, Policastro |  |  |  | Yes |  | Not Started | 42
8 | Database's management | Sprint 2 | " " | 2020-12-09 | 2020-12-11 | Yes |  | High | Complete | 13 | Yes
12 | Maintainers' availability's check | Sprint 2 | " " | 2020-12-13 | 2020-12-15 | Yes |  | High | Complete | 13 | Yes
4 | Standard procedure | Sprint 2 | " " | 2020-12-14 | 2020-12-15 | Yes |  | Medium | Complete | 8 | Yes
17 | Activity's details | Sprint 2 | " " | 2020-12-12 | 2020-12-13 | Yes |  | Medium | Complete | 8 | Yes
18 | Refactoring of the first release | Sprint 2 | " " | 2020-12-07 | 2020-12-11 | No |  | Medium | Complete |  | Yes
21 | Refactoring of backend's code | Sprint 2 | " " | 2020-12-15 | 2020-12-16 | No |  | Low | Complete |  | Yes
11 | Activity's info visualization | Sprint 2 | " " | 2020-12-12 | 2020-12-14 | Yes |  | Low | Complete | 3 | Yes
|  |  | Marzolo, Oro, Pagliara, Policastro |  |  |  | No |  | Not Started
5 | Workspace notes's management | " " | " " |  |  | Yes |  | Low | Not Started
6 | Maintaiance's procedure's report | " " | " " |  |  | Yes |  | Medium | Not Started
13 | Assigned activity's notification | " " | " " |  |  | Yes |  | Medium | Not Started
|  |  | Marzolo, Oro, Pagliara, Policastro |  |  |  | No |  | Not Started
14 | EWO's management | " " | " " |  |  | Yes |  | High | Not Started
15 | Maintainer's acitivities' interruption | " " | " " |  |  | Yes |  | Medium | Not Started
16 | EWO's list visualization | " " | " " |  |  | Yes |  | Low | Not Started
19 | Redesign the login logic in order to allow access from multiple devices | " " | " " |  |  | No |  | Low | Not Started
20 | Add the ability to schedule a periodic activity | " " | " " |  |  | No |  | Low | Not Started