## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | SPRINT REVIEW | COMPLETED
#1 - Users' management | 21 | [12 empty] | 1
Design the database for user's management | 3 | Oro Carmine, Policastro Pasquale | Done | 4.5 | DAY 1: 3 |  | DAY 1
Create the administration page with the user registration form | 4 | Marzolo Alice, Pagliara Lorenzo | Done | 3 | DAY 1: 2; DAY 2: 3; DAY 3: 1 |  | DAY 3
Create a login page | 1 | Marzolo Alice, Pagliara Lorenzo | Done | 2 | DAY 3: 1; DAY 4: 0.5 |  | DAY 4
Create the backend logic for the registration/login process | 5 | Oro Carmine, Policastro Pasquale | Done | 5 | DAY 2: 6; DAY 3: 4 |  | DAY 3
Create the backend logic for users management | 3 | Oro Carmine, Policastro Pasquale | Done | 3 | DAY 3: 0.5; DAY 4: 1.5 |  | DAY 4
Backend-Frontend integration | 5 | Marzolo Alice, Pagliara Lorenzo | Done | 4 | DAY 4: 4; DAY 5: 2 |  | DAY 5
#2 - Role's assignment | 2 | [12 empty] | 0.5
Redesign the database in order to add the users' role | 0.5 | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 4: 0.5 |  | DAY 4
Create the frontend UI and logic for the users' role assignment | 0.5 | Marzolo Alice, Pagliara Lorenzo | Done | 0.5 | DAY 5: 0.5; DAY 6: 0.5 |  | DAY 6
Handle the UI's view with respect of the users' role | 0.5 | Marzolo Alice, Pagliara Lorenzo | Done | 1 | DAY 6: 2 |  | DAY 6
Create the backend logic for the users' role assignment | 0.5 | Oro Carmine, Policastro Pasquale | Done | 1 | [10 empty] | DAY 4 | bar: DAY 4
#3 - Maintainers' competences' assignment | 5 | [12 empty] | 2
Redesign the database in order to add the users' competences | 1 | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 4: 0.5 |  | DAY 4
Create the backend logic for the users' competences assignment | 2 | Oro Carmine, Policastro Pasquale | Done | 1.5 | DAY 5: 2.5 |  | DAY 5
Redesign the registration form in order to assign to the users the competences | 2 | Marzolo Alice, Pagliara Lorenzo | Done | 1.5 | [10 empty] | DAY 8 | bar: DAY 8
#7 - Access log | 2 | [12 empty] | 0.25
Create an accesses logger table in the database | 0.5 | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 5: 0.5 |  | DAY 5
Create the backend logic for the access logger | 0.5 | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 6: 0.5 |  | DAY 6
Add an accesses register in the administration page | 1 | Marzolo Alice, Pagliara Lorenzo | Done | 1 | DAY 8: 0.5 |  | DAY 8
#9 - Planned activities' management | 21 | [12 empty] | 2
Redesign the database in order to add the activities | 1 | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 6: 0.5 |  | DAY 6
Create the backend logic for the activities' management | 4 | Oro Carmine | Done | 2 | DAY 6: 1.5 |  | DAY 6
Create the frontend UI and logic for the activities' management | 4 | Marzolo Alice, Pagliara Lorenzo | Done | 2 | DAY 8: 3.5 |  | DAY 8
Create the backend logic for managing the activities' assignments | 4 | Policastro Pasquale | Done | 2 | DAY 6: 1.5 |  | DAY 6
Create the frontend UI and logic for the activities' assignments | 8 | Marzolo Alice, Pagliara Lorenzo, Oro Carmine, Policastro Pasquale | Done | 6 | DAY 8: 2; DAY 9: 5 |  | DAY 9
#10 - Activities List's visualization | 5 | [12 empty] | 0.5
Create the backend logic in order to get the Activities' List (ordered by week) | 1 | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 7: 0.5 |  | DAY 7
Create the frontend UI and logic in order to see the Activities' List (ordered by week) | 4 | Marzolo Alice, Pagliara Lorenzo | Done | 2 | DAY 7: 1.5; DAY 8: 2.5 |  | DAY 8
TOTAL |  |  |  | 45 | 5 | 9 | 6.5 | 8 | 5.5 | 6.5 | 2 | 9.5 | 5 | 5
EFFECTIVE EFFORT |  |  |  | 45 | 40.5 | 40.5 | 32.5 | 25.5 | 19.5 | 13 | 12.5 | 6 | 0 | 5
ESTIMATED EFFORT |  |  |  | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0 | 5