## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | SPRINT REVIEW | COMPLETED
#18 Refactoring of the first release | [13 empty] | 1
Refactoring of backend's code |  | Pagliara Lorenzo, Policastro Pasquale | Done | 6 | DAY 1: 6.5 |  | DAY 1
Regression test |  | Marzolo Alice, Oro Carmine | Done | 6 | DAY 1: 6 |  | DAY 1
Unit Test |  | Oro Carmine, Policastro Pasquale, Pagliara Lorenzo, Marzolo Alice | Done | 4 | DAY 2: 1.75; DAY 3: 2 |  | DAY 3
Testing case documentation |  | Pagliara Lorenzo, Marzolo Alice | Done | 2 | DAY 4: 2 |  | DAY 4
#8 - Database's management | 13 | [12 empty] | 0.5
Redesign the database in order to add all the info related to the activities |  | Oro Carmine, Policastro Pasquale | Done | 2 | DAY 2: 1.75 |  | DAY 2
Create the frontend UI for the repository manager |  | Marzolo Alice, Pagliara Lorenzo | Done | 5 | DAY 2: 2.75; DAY 3: 3 |  | DAY 3
Create the backend logic for managing the activities' info |  | Oro Carmine, Policastro Pasquale | Done | 3 | DAY 2: 2.5 |  | DAY 2
Testing (Unit Test/API Testing) |  | Oro Carmine, Policastro Pasquale | Done | 3 | DAY 3: 1.75; DAY 4: 1.75 |  | DAY 4
#17 - Activity's details | 8 | [12 empty] | 0.5
Redesign the database in order to give more details to the activities |  | Oro Carmine, Policastro Pasquale | Done | 1.5 | DAY 5: 0.75 |  | DAY 5
Create the backend logic for adding/removing infos from an activity |  | Oro Carmine, Policastro Pasquale | Done | 1.5 | [10 empty] | DAY 5 | bar: DAY 5
Create the frontend logic and redesign the activities management's UI according to add the new informations |  | Marzolo Alice, Pagliara Lorenzo | Done | 4 | DAY 6: 4 |  | DAY 6
Testing (Unit Test/API Testing) |  | Oro Carmine, Policastro Pasquale | Done | 1 | [10 empty] | DAY 5 | bar: DAY 5
#11 - Activity's info visualization | 3 | [12 empty] | 0.5
Create the backend logic for retrieving all the activities info |  | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 5: 0.5 |  | DAY 5
Redesign the UI page to view the newly added informations |  | Marzolo Alice, Pagliara Lorenzo | Done | 1 | DAY 7: 0.75 |  | DAY 7
Testing (Unit Test/API Testing) |  | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 5: 0.25 |  | DAY 5
#12 - Maintainers' availability's check | 13 | [12 empty] | 1
Redesign the database in order to add the maintainers' availabilities |  | Oro Carmine, Policastro Pasquale | Done | 1.5 | DAY 6: 1.5 |  | DAY 6
Create the backend logic for managing the maintainers' availabilities |  | Oro Carmine, Policastro Pasquale | Done | 1.5 | [10 empty] | DAY 6 | bar: DAY 6
Redesign the UI page in order to manage the maintainers' availabilities |  | Marzolo Alice, Pagliara Lorenzo | Done | 5 | DAY 7: 1; DAY 8: 3 |  | DAY 8
Testing (Unit Test/API Testing) |  | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 6: 0.5 |  | DAY 6
#4 Standard procedure | 8 | [12 empty] | 0.5
Redesign the database in order to add the SMP files |  | Oro Carmine, Policastro Pasquale | Done | 1.5 | [10 empty] | DAY 7 | bar: DAY 7
Create the backend logic for managing the SMP files |  | Oro Carmine, Policastro Pasquale | Done | 2.5 | DAY 7: 2 |  | DAY 7
Create the frontend logic for upload/download a SMP file |  | Marzolo Alice, Pagliara Lorenzo | Done | 2 | DAY 8: 2 |  | DAY 8
Testing (Unit Test/API Testing) |  | Oro Carmine, Policastro Pasquale | Done | 0.5 | DAY 8: 0.5 |  | DAY 8
#21 Refactoring of the second release | [13 empty] | 0.25
Refactoring of frontend's code |  | Pagliara Lorenzo, Marzolo Alice | Done | 6 | DAY 8: 2; DAY 9: 4.5 |  | DAY 9
Refactoring of backend's code |  | Oro Carmine, Policastro Pasquale | Done | 5 | DAY 9: 4.5 |  | DAY 9
EFFECTIVE EFFORT |  |  |  | 67 | 55 | 50 | 41 | 36 | 31 | 23.5 | 18.5 | 11 | 0
ESTIMATED EFFORT |  |  |  | 67 | 59.5556 | 52.1111 | 44.6667 | 37.2222 | 29.7778 | 22.3333 | 14.8889 | 7.4444 | 0
EFFECTIVE WORK'S HOURS |  |  |  | 63.5 | 6 | 8.75 | 6.75 | 3.75 | 3.5 | 7 | 4.75 | 7.5 | 9